## Sheet1
| Non Editable | Editable | Editable | Editable | Non Editable |  |  | Editable | Editable | Editable | Remove | Editable | Editable | Editable | Editable | Editable | Editable | Editable | Editable
# | Denial Codes | Descriptions | # of Denial | Total Balance ($) | Highest $ Impact - Insurance |  |  | Ins. Balance ($) | $ Impact (%) | Observation | Data | Category | Action | Feedback / Response | Responsibility | Discussion Date | ETA | Closed Date | Status
1 | B7 | This provider was not certified/eligible to be paid for this procedure/service on this date of service | 137 | 113243.17 | WELLPOINT - AMERIGROUP TX | WELLPOINT - AMERIGROUP TX | WELLPOINT - AMERIGROUP TX | 90944.88 | 80.31% | • Per reviewing the The most number claims denied are for Pathology. | Link | Review | • Request the AR team to call the payer and verify why provider is deemed not eligible for payment | Client Feedback - WV Pay hold | Tarshann | 2026-10-02 | 2026-10-09 | - | Yet to Discuss
2 | 252 | An attachment/other documentation is required to adjudicate this claim/service. | 166 | 104698.81 | UHC OHIO MEDICAID COMMUNITY PLAN | UHC OHIO MEDICAID COMMUNITY PLAN | UHC OHIO MEDICAID COMMUNITY PLAN | 50384.45 | 48.12% | • Per review all of denied claims are for WH Panel/Male STI Panel. | Link | Appeal / MR | • Submit the Patients Medical Records to the insurance company via the appropriate channels.(Eg: Portal, Fax) | - | Tarshann | 2026-10-02 | 2026-10-09 | - | Closed
3 | 49 | This is a non-covered service because it is a routine/preventive exam or a diagnostic/screening procedure done in conjunction with a routine/preventive exam | 129 | 98393.84 | TENNESSEE MEDICARE | TENNESSEE MEDICARE | TENNESSEE MEDICARE | 45400.36 | 46.14% | • Per reviewing the The most number claims denied are for Pathology. | Link | Appeal / MR | • Submit a formal appeal/reconsideration addressing each denial reason. | - | Tarshann | 2026-10-02 | 2026-10-09 | - | Deferred
4 | 150 | Payer deems the information submitted does not support this level of service. | 44 | 75113.23 | UNITED HEALTHCARE |  |  | 46588.17 | 62.02% | • Per reviewing the The most number claims denied are for Pathology. | Link | Review | • Submit the Patients Medical Records to the insurance company via the appropriate channels.(Eg: Portal, Fax) | - | Tarshann | 2026-10-02 | 2026-10-09 | - | Yet to Discuss
5 | 204 | This service/equipment/drug is not covered under the patient's current benefit plan | 157 | 74272.65 | VIRGINIA BLUE CROSS |  |  | 32215.44 | 43.37% | • Per review majority of denied claims are for Toxicology panel. | Link | Review | • Check Eligibilty and see whether there is another active coverage for the Patient. • Request the AR team to contact the payor and verify the exact reason of the denial and if it is a Diagnosis issue rebill the claim with the Correct Diagnosis code. | FVI, Z4U claims - processed as OON Client Action - we are working with our network manager to fix this LRN Feedback - Pending response from client. | Tarshann | 2026-10-02 | 2026-10-09 | - | Closed
6 | 22 | This care may be covered by another payer per coordination of benefits. | 62 | 74198.22 | MOUNTAIN STATE BLUE SHIELD WV FEDERAL EMPLOYEE PROGRAM |  |  | 54922.84 | 74.02% | • 36 Patients Info Required | Link | Review/ Reprocess | • Use online portals/ Insurance call to identify primary payer & rebill the claim. • If a primary payer cannot be identified need to be escalated to CIP. | COB Denials. Problem: BCBS required patients to call them and update their COB. Patient has many payers as primary. Client's process: Place the claim on patient calls, Jay calls and asks the patient to update. Client's Process Weaknesses: 1) It takes several months to reach the patient, many calls go to VM/no response. 2) Even when pt confirms to call or called > no result. 3) It takes the AR team a long time to return to the claim and send for reprocessing. LRN Feedback - According to Clients feedback, claims has been worked and remaining is pending to be cleared from the AR. | Tarshann | 2026-10-02 | 2026-10-09 | - | Deferred
7 | 16 | Claim/service lacks information or has submission/billing error(s). | 129 | 63369.28 | UHC OHIO MEDICAID COMMUNITY PLAN |  |  | 13699.64 | 21.62% | • As per reviewing the claims unable to identify as why claims denied as no remark code was available. •Majority of the denials belong to WH Panel/Male STI Panel claims. | Link | Review | • Request the AR team to call the payer and find out why these claims denied and fix the claims accordingly. | - | Tarshann | 2026-10-02 | 2026-10-09 | - | Closed
8 | 197 | Precertification/authorization/notification/pre-treatment absent. | 112 | 56999.91 | HIGHMARK BCBS DELAWARE (MEDICAID PLAN) |  |  | 20616.48 | 36.17% | • Majority of the denials belong to Toxicology claims • As per checking All services for out-of-network providers require PA, except emergency care, out-of-area urgent care, or out-of-area dialysis. | Link | Review | • Check in LIMS if the pre-authorization number is avilable in the records. • Call and verify if the payer approves retro authorization. If not, submit an appeal through the appropriate channel. • Suggesting to Adjust off if no retro authorization can be applied with Payer. | All claims have denied dates before AP contract eff date 03/12/2026 - okay to adjust Client Action - write-off LRN Feedback - As of today Insurance balance still remaining without being written off. | Tarshann | 2026-10-02 | 2026-10-09 | - | Deferred
Formulas:
Editable = [Editable]+7