## Summary
AR Workbench – Requirements Test Report
Requirement source | AR_Workbench_Developer_Handoff_v1.0.docx (v1.0, 29 Sep 2026); mockup LRN_Denial_AR_Workbench_Demo_Account.html
Application | https://www.lrnanalytics.com/ARWBTest/ (Test) – lab Inhealth_DTR
Tested as | Phase 1: ARWBInhealthSA (System Administrator). Phase 2 role workflow: ARAgent1, QA1, TeamLead, RCMManager, ClinicViewer (Insight Family Practice), AccountManager (Client Viewer)
Test date | 15 Oct 2026
Data snapshot | Sync run #3, 08 Oct 2026 – 84,074 claims / 151,186 CPT lines
Method | Phase 1 read-only UI walkthrough + API reconciliation of all 84,074 claims. Phase 2 (user-approved) end-to-end role workflows on 10 test claims — see 'Role Workflow Tests'.
Status | # Test Cases | % of Total
Pass | 34 | 50%
Fail | 12 | 17.65%
Partial | 14 | 20.59%
Blocked | 3 | 4.412%
Not Executed | 4 | 5.882%
N/A (Phase 2) | 1 | 1.471%
Total | 68 | 100%
Pass rate (of executed) | 56.67% | Executed = Pass + Fail + Partial
Module | Total | Pass | Fail | Partial | Blocked | Not Executed | N/A (Phase 2)
Data Sync & Grain | 3 | 3 | 0 | 0 | 0 | 0 | 0
Denial Insights | 5 | 2 | 1 | 2 | 0 | 0 | 0
Claim Detail | 3 | 1 | 0 | 2 | 0 | 0 | 0
AR Queue Logic | 12 | 10 | 1 | 1 | 0 | 0 | 0
Configuration | 1 | 0 | 0 | 1 | 0 | 0 | 0
Roles & Access | 3 | 0 | 1 | 2 | 0 | 0 | 0
Denial Logic | 6 | 3 | 1 | 0 | 1 | 0 | 1
Weekly Re-Sync | 5 | 0 | 0 | 1 | 1 | 3 | 0
Auto Adjustments | 3 | 3 | 0 | 0 | 0 | 0 | 0
Financial Fields | 5 | 0 | 3 | 1 | 1 | 0 | 0
Follow-Up | 2 | 2 | 0 | 0 | 0 | 0 | 0
Attachments | 5 | 0 | 3 | 1 | 0 | 1 | 0
Write-Off Approval | 2 | 1 | 0 | 1 | 0 | 0 | 0
Escalation / Reassignment | 2 | 2 | 0 | 0 | 0 | 0 | 0
Assignment | 1 | 1 | 0 | 0 | 0 | 0 | 0
CIP Workflow | 6 | 5 | 1 | 0 | 0 | 0 | 0
User Management | 3 | 1 | 1 | 1 | 0 | 0 | 0
Export / Import | 1 | 0 | 0 | 1 | 0 | 0 | 0
Total | 68 | 34 | 12 | 14 | 3 | 4 | 1
Key findings
1. Queue classification engine is correct: all 84,074 claims sit in exactly one queue and every Closed, Patient AR, Non-Responder, Denied and Partially Paid/Adjusted rule reconciles with zero exceptions.
2. Work-queue feed and 'Claims Awaiting Assignment' KPI include Non-Collectible, Unbilled (and for the KPI, Closed/Patient AR) claims — contrary to §3.2 (DEF-05, DEF-06).
3. Two conflicting Non-Collectible lists exist (Workbench list vs Denial Code Master) — needs a single source of truth (DEF-07).
4. Financial fields not functional: Revenue Expectation is $0 for every claim (no fee schedule), so Potential Recovery / Recovery Status are blocked; Recovered Amount includes adjustments (DEF-11, DEF-12).
5. Attachments on follow-ups, document categories and the Document Vault are not built (DEF-13, DEF-14).
6. 48% of denied claims fall to 'Other' because 50 codes (incl. 216) are unmapped — waiting on business categorization (DEF-09).
7. CRITICAL: client users (Clinic & Client Viewer) can open claim pages directly and read internal agent/QA notes (DEF-15).
8. Role workflows largely work end-to-end: assignment, QA approve/reject/rework, write-off approval, CIP two-level approval, client response with re-escalation and return to agent, escalation/reassignment requests (30 role steps, see 'Role Workflow Tests').
9. Role gaps: agent cannot mark write-off as posted (DEF-17); Clinic Viewer cannot respond to CIPs (DEF-18); QA API exposes restricted queues (DEF-16); Manager cannot maintain NC list (DEF-08).
10. Still not executed: weekly re-sync scenarios (need a new sync file) and Azure Blob HIPAA controls (infra review). 19510788 was left auto-adjusted and unposted to verify re-sync flagging on the next sync.
Role workflow results (Phase 2)
Role | Steps | Pass | Fail | Partial
System Administrator | 3 | 3 | 0 | 0
AR Agent | 8 | 7 | 0 | 1
QA Reviewer | 3 | 2 | 0 | 1
Team Lead | 5 | 5 | 0 | 0
Clinic Viewer | 3 | 1 | 2 | 0
Client Viewer | 3 | 2 | 1 | 0
RCM Manager | 5 | 4 | 1 | 0
Total | 30 | 24 | 4 | 2

## Test Cases
Test Case ID | Module | Requirement Ref | Priority | Test Scenario | Test Data / Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Defect / Obs Ref
TC-001 | Data Sync & Grain | §2.1 / Feature #1 | High | Full claim-level master file is synced for the lab | Lab Inhealth_DTR; Data Processing run #3 (R20261005INH3267 ... 09.22–09.28.2026.csv) | 1. Open Data Processing. 2. Review Run history and source counters. 3. Reconcile claim count to queue totals via API. | Every claim in the claim-level master file is loaded (not only insight-linked claims); line-level file also read. | Run #3 succeeded: 84,074 claims (1,206 new, 1,802 updated, 81,066 unchanged, 0 dropped); 151,186 CPT lines read. 84,074 = sum of all queue counts. Header field 'Master File Loaded' shows '—'. | Pass | OBS-01
TC-002 | Data Sync & Grain | §2.1 | Medium | Sync cadence is weekly and aligned with master refresh | Run history; Nightly Queue Snapshots | 1. Review run history dates. 2. Review nightly snapshot table. | Weekly sync runs recorded; nightly recalculation of aging / TFL / re-follow-up. | Syncs on Sep 30 and Oct 08, 2026; nightly snapshots Oct 06–Oct 15 present. | Pass
TC-003 | Data Sync & Grain | §2.1, §3 | High | Every list, queue and count is at claim grain; each claim sits in exactly one financial queue | All 84,074 claims pulled via claims API (read-only) | 1. Pull all claims. 2. Check unique claim keys. 3. Sum queue/sub-queue counts. | Unique claim count = total; each claim in exactly one queue. | 84,074 records, 84,074 unique claim keys; queue counts sum to 84,074 with no overlaps. | Pass
TC-004 | Denial Insights | §2.2 | High | Dashboard 'Latest Denial Analysis Report insights' shows the CURRENT week's insights | Current week (Oct 14, 2026) has 1 uploaded Key Observation (CO-216) | 1. Open Dashboard. 2. Compare insight list with Data Processing > Current week. | Dashboard shows the same current-week insights as Data Processing, with description populated. | Dashboard lists 5 system-generated codes (216, 252, 31, 27, 96) while Data Processing current week shows only the uploaded CO-216 insight. Dashboard Description column shows '—' for every row. | Fail | DEF-01, DEF-02
TC-005 | Denial Insights | §2.2 | Medium | Data Processing shows current + previous week insights, unresolved items only | Data Processing > Denial Analysis Report | 1. Open Current week tab. 2. Open Previous week tab. 3. Check 'still open' counts. | Two tabs (current & previous); counts reflect only unresolved / unassigned items. | Current week (Oct 14) and Previous week (Sep 28) tabs present; open counts shown as 'X of Y'. Previous-week (system-generated) rows have Description '—' for all codes. | Partial | DEF-02
TC-006 | Denial Insights | §2.2 | High | Clicking an insight routes to the filtered claim set in the Work Queue for bulk assignment | Insight CO-216 (Still open 1,699) | 1. Data Processing > Current week. 2. Click 'Route to Work Queue' on CO-216. | Work Queue opens filtered to the insight's unassigned open claims; count equals insight's open count. | Work Queue opened with filters Denial Code = CO-216, Workflow Status = Unassigned, Open AR only; 1,700 records returned vs 1,699 on the insight (1 claim carries 216 as a secondary code). | Partial | OBS-02
TC-007 | Denial Insights | §2.2 | Medium | Insight counts cover all payers; Highest-impact payer is informational only | Insight CO-216 | 1. Compare # of denials vs. Ins. # of denials for top payer. | Count and balance cover all payers; top payer is not used as a filter. | CO-216: 2,051 denials / $714,194.50 across all payers; BCBS-MT shown as highest-impact payer (2,044) for information. Routing did not apply a payer filter. | Pass
TC-008 | Denial Insights | §2.2, AT-7, Feature #3 | High | Assigned claims are deducted from insight outstanding count/balance | CO-216: 2,051 total; 10 already assigned | 1. Read insight 'Still open'. 2. Independently recompute open, unassigned claims with primary denial 216. | Insight shows only the unassigned remainder. | Insight shows Still open 1,699 / $591,207.62. Independent recomputation: 1,699 open, unassigned claims with primary denial 216 (assigned claims excluded). | Pass
TC-009 | Claim Detail | §2.3 | Medium | Denial Info shows the claim's primary denial (code, description, category, classification) | Claim 19448764 (curated denial 'CO11, CO252') | 1. Open claim. 2. Open Denial Info tab. | Primary code, description, category and classification populated. | Primary Denial Code '11 (as received CO11)', Category 'Coding-Related Denials' shown. Denial Reason '—'; All Denial Codes '—' although claim carries CO11, CO252; Line-Level Codes rendered as '11252' (two codes concatenated without separator). | Partial | DEF-03
TC-010 | Claim Detail | §2.3, Feature #4 | Medium | CPT Line-Level Detail has an expand control per CPT showing line-level denial code (prefix retained), description, classification | Claim 19448764 (7 CPT lines) | 1. Open CPT / Line Detail tab. 2. Look for expand control on each CPT. | Each CPT row expandable; reveals line denial code with original prefix, description and classification. | Line denials appear as an always-visible sub-row ('↳ Denial CO11 · Mar 24, 2026') — no expand control, no description/classification on this tab. Description and category are available in the separate 'Line-Level Denials' table under Denial Info. Prefix retained for display. | Partial | DEF-04
TC-011 | Claim Detail | §2.3 | Medium | Line-level data does not drive queue placement | Claim 19448764: lines Denied CO11/CO252 + 5 Partially Adjusted lines | 1. Compare line statuses with claim AR Queue. | Queue derived from claim-level primary denial only. | Claim placed in Denied · Possible Collectible based on claim-level primary 11; line-level partial adjustments did not affect placement. | Pass
TC-012 | AR Queue Logic | §3.1, AT-1 | High | Closed – Fully Paid: Ins Bal = 0 and Pt Bal = 0; not fed to work queue | All claims (API) | 1. Check every Closed claim balance. 2. Check no zero-balance claim sits outside Closed. 3. Check queue is non-priority. | All Closed – Fully Paid claims have zero balances; not in active work-queue feed. | 42,502 claims; 0 with any balance; 0 zero-balance claims outside Closed; queue flagged non-priority (not auto-fed). | Pass
TC-013 | AR Queue Logic | §3.1 | High | Closed – Fully Adjusted: fully adjusted, no balance | All claims (API) | 1. Check balances of Closed – Fully Adjusted claims. | Zero insurance and patient balance. | 21,088 claims, all zero balance. | Pass
TC-014 | AR Queue Logic | §3.1, AT-2 | High | Non-Responder: Ins Bal > 0, no payment/denial/adjustment; auto-fed to work queue | All claims (API) | 1. Check Non-Responder claims for denial codes and balance. 2. Check priority flag. | All have Ins Bal > 0 and no denial; queue is auto-fed. | 2,627 claims; 0 with a denial code; 0 with zero Ins Bal; queue is priority (auto-fed). 2 claims have source status 'Patient Responsibility'. | Pass | OBS-03
TC-015 | AR Queue Logic | §3.1, §4.1 | High | Denied – Possible Collectible: Ins Bal > 0, primary denial NOT on NC List | NC List = 197, 242, 257, 288, 27, 31 | 1. For each Denied PC claim, strip prefix from primary code and test against NC List. | No Denied PC claim has an NC primary code. | 4,280 claims; 0 with NC primary. 100 claims carry an NC/terminal code as a SECONDARY code in the curated column (e.g., 19509114 'PI5, PR242') and remain Possible Collectible — consistent with interim 'first code = primary' rule; terminal-denial override is Phase 2. | Pass | OBS-04
TC-016 | AR Queue Logic | §3.1, §3.2, AT-3 | High | Denied – Non-Collectible: primary on NC List; visible only to Admin/Mgr/TL | Primary 197 / 27 / 31 etc. | 1. Verify placement via API. 2. Verify visibility as AR Agent / QA. | Placed in Denied – Non-Collectible; hidden from Agent/QA. | 751 claims placed correctly (all NC primary). Phase 2: ARAgent1 sees only its own 18 claims; NC queue query returns 0 and other claims 404 for the agent. Team Lead sees NC (749). QA Reviewer UI is blocked, but the claims API returns NC claims to QA (DEF-16). | Partial | DEF-16
TC-017 | AR Queue Logic | §3.1 | High | Partially Paid – Possible Collectible / Non-Collectible split uses the same NC List | All claims (API) | 1. Check NC flag vs sub-queue. | PC: primary not on NC List; NC: primary on NC List. | 302 PC (0 NC primaries) / 8 NC (all NC primaries). | Pass
TC-018 | AR Queue Logic | §3.1 | High | Partially Adjusted: no denial, some CPTs adjusted, Ins Bal > 0 | All claims (API) | 1. Check denial code and balance on Partially Adjusted claims. | No denial; Ins Bal > 0; auto-fed. | 61 claims; 0 with denial; all Ins Bal > 0; priority queue. | Pass
TC-019 | AR Queue Logic | §3.1, AT-6 | High | Patient AR: Pt Bal > 0 and Ins Bal = 0; denials ignored | All claims (API) | 1. Check all Patient AR claims. 2. Check no Pt-only-balance claim outside Patient AR. | All Patient AR claims meet rule; none misplaced, even when a denial is present. | 11,349 claims, all Pt Bal > 0 & Ins Bal = 0; 0 misplaced. None of these claims carries a denial code in the claim data, so 'denial present' variant could not be exercised. | Pass | OBS-05
TC-020 | AR Queue Logic | §3.1, Features #7, #8 | High | Workflow queues exist: CIP Pending, CIP Response Received, Re-Follow-Up (Unresolved / New Denials), Submitted for QA, QA Rejected, Completed, Auto Adjustments | Queue taxonomy (queues API) | 1. Review queue list. | All workflow queues and sub-queues defined. | All present, incl. Re-Follow-Up → Unresolved Claims / New Denials and Auto Adjustments → System Auto-Adjusted / Approved Write-Offs – Pending Posting. Extra queues not in spec: 'Unbilled (Not Yet Billed)' (1,102) and 'Status Change Verification'. | Pass | OBS-06
TC-021 | AR Queue Logic | §3.2 | High | Only unresolved claims in the 4 Possible Collectible queues auto-flow into the Work Queue for assignment | Nav badge 'Denial & AR Work Queue' = 9,054; Dashboard 'Claims Awaiting Assignment' = 83,986 | 1. Reconcile unassigned counts by queue. 2. Compare with badge and dashboard KPI. | Awaiting-assignment count = unassigned claims in Non-Responder, Denied PC, Partially Paid PC, Partially Adjusted only (7,193). | Badge 9,054 = 7,193 PC + 759 Non-Collectible (751 Denied + 8 Partially Paid) + 1,102 Unbilled. Dashboard KPI 'Claims Awaiting Assignment' = 83,986 counts every unassigned claim, including 63,583 Closed and 11,349 Patient AR. | Fail | DEF-05, DEF-06
TC-022 | Configuration | §3.2, Feature #2 | High | Non-Collectible list maintained in settings and drives the Denied & Partially Paid splits | Master Values > Workbench Lists > Non-Collectible Denial Codes | 1. Open list. 2. Compare with Denial Code Master 'Non-Collectible' flags. | Single configurable NC list, stored without prefix, used by the queue engine. | Workbench list (6 codes: 197, 242, 257, 288, 27, 31) is maintainable and used by the queue engine. However, Denial Code Master flags a DIFFERENT set of 8 NC codes (29, 119, 193, 197, 204, 242, 243, 279) with an 'Apply Non-Collectible codes' action — two conflicting sources. | Partial | DEF-07
TC-023 | Roles & Access | §10 (Maintain NC & Auto-Adjust lists) | Medium | AR/RCM Manager can maintain NC and Auto-Adjust lists | App navigation role config | 1. Inspect role access for Master Values. | Sys Admin and AR/RCM Manager can maintain. | Master Values (incl. Workbench Lists) is restricted to System Administrator only ('Administrators only'); RCM Manager has no access. | Fail | DEF-08
TC-024 | Roles & Access | §3.2, AT-3 | High | Restricted (overall AR) queues visible only to Admin / Mgr / TL; they can pull any claim for special projects | Admin session | 1. As Admin, view all queues and assign. 2. As Agent/QA, confirm restricted queues hidden. | Admin/Mgr/TL see and assign from any queue; Agent/QA cannot see Closed / NC queues. | Admin, RCM Manager and Team Lead see and assign from all queues (TL: 84,074 claims incl. 749 NC / 21,090 Closed-Adjusted). AR Agent restricted server-side to own claims. QA Reviewer: Work Queue page blocked, but claims API returns all 84,074 claims incl. restricted queues. | Partial | DEF-16
TC-025 | AR Queue Logic | §3.2 | High | QA Rejected claims auto-assigned to the agent who worked them | Claim 19091270 | 1. Open claim timeline and assignment fields. | Rejected claim assigned back to the submitting agent. | Submitted by ARAgent1, rejected by QA1 (Financial Update Error); AssignedAgentUser = ARAgent1. Note: work-queue API returns AssignedAgentName = null for this claim. | Pass | OBS-07
TC-026 | AR Queue Logic | §3.2 (To confirm) | Low | Evaluation precedence when a claim meets more than one rule | All claims | 1. Check for claims meeting multiple rules. | Deterministic precedence (recommended Closed → Patient AR → Denied → Partially Paid → Partially Adjusted → Non-Responder). | No claim found in more than one queue; precedence behaviour consistent with recommended order in observed data. Formal precedence still an open item (#4). | Pass
TC-027 | Denial Logic | §4.1 | High | Primary denial = curated 'Denial Code' column (interim) | Settings API | 1. Read settings PrimaryDenialSource / FallbackToLine. | Curated column used; no line-level fallback. | PrimaryDenialSource = CuratedColumn; PrimaryDenialFallbackToLine = 0. | Pass
TC-028 | Denial Logic | §4.1, Feature #15 | Low | Denial-hierarchy ranking table to derive primary denial (terminal codes override) | — | — | Configurable ranking table; e.g., 204/197 override other codes. | Phase 2 — awaiting mapping from business owner. Not tested. | N/A (Phase 2)
TC-029 | Denial Logic | §4.2, AT-4, Feature #5 | High | CARC group prefix (CO/PR/PI/OA) stripped for mapping | PR204 (25 claims), CO204 (13 claims); PRA1, PIB11 | 1. Compare category for prefixed variants of the same code. | PR 204 and CO 204 both map to 204 and the same category. | PR204 and CO204 both → 204 → Medical Necessity. PRA1→A1, PIB11→B11, COB12→B12 normalised correctly. 'CR96' (CR group) is not stripped and lands in Unmapped/'Other' while CO/PR/PI96 map to Medical Necessity. | Pass | OBS-08
TC-030 | Denial Logic | §4.2, AT-5 | Medium | RARC codes keep their letter (e.g., N57, M127, MA130) | Claim data and Denial Code Master | 1. Search for N57 / RARC codes. | Stored and mapped as N57 (letter retained). | No N57 / M127 / MA130 in claim data or Denial Code Master. Only RARC-style code found, N857 (4 claims), is retained as 'N857' but is unmapped. Test data needed. | Blocked | Test data
TC-031 | Denial Logic | §4.3 | High | Denial categorization for all denial codes loaded into the Denial-Action master | Workbench Category Map / Unmapped Codes | 1. Review category map coverage. 2. Review Unmapped Codes. | Every primary denial code on synced claims has a category. | Only 36 codes mapped; 50 primary codes unmapped (incl. 216 – 1,708 claims / $594,638.84; A1 – 222 claims). 2,534 of 5,280 denied claims (48%) fall to 'Other'. Depends on open item #2 (categorization from business owner). | Fail | DEF-09
TC-032 | Denial Logic | §4.2 | Low | Line-level display keeps original prefix but is not used for mapping | Claim 19448764 | 1. View line-level denials. | Prefixed value shown; mapping uses stripped code. | Lines show CO11 / CO252; claim maps on stripped 11. | Pass
TC-033 | Weekly Re-Sync | §5, AT-10 | High | Assigned, not-yet-worked claim whose denial changes: update silently; if new primary is NC, auto-process and remove from agent queue | Requires a sync with changed denial data | 1. Assign claim. 2. Load sync file with new (NC) denial. 3. Check agent queue. | Denial updated without reassignment; NC claim auto-processed and removed. | Not executed — needs a controlled re-sync. App has a 'Status Change Verification' queue for claim-STATUS changes on assigned claims (not in spec). | Not Executed | OBS-06
TC-034 | Weekly Re-Sync | §5, AT-9, Feature #7 | High | Worked claim (QA/Completed/QA Rejected) receives a new denial → after QA completes, moves to Re-Follow-Up – New Denials, unassigned, history intact | Requires a sync with a new denial on a completed claim | 1. Complete claim. 2. Re-sync with new denial. | Claim in Re-Follow-Up – New Denials, unassigned, full history. | Queue exists (0 claims). Not executed — needs controlled re-sync. | Not Executed
TC-035 | Weekly Re-Sync | §5, §3.1 | High | Followed-up claim with no reply/action for 45 days → Re-Follow-Up – Unresolved Claims | RefollowupDays = 45 | 1. Identify claims with last touch ≥ 45 days. | Claims ≥ 45 days since last touch appear in Unresolved queue. | Setting = 45. Earliest follow-up in system is Oct 07, 2026, so no claim qualifies yet. Assignment page separately lists '6,066 claims untouched for 45+ days' — these are never-worked claims, which by spec are not Re-Follow-Up. | Blocked | OBS-09
TC-036 | Weekly Re-Sync | §5, §6, AT-12, Feature #9 | High | Auto-adjusted / approved write-off claim still open on next sync → flagged, returned to Auto Adjustments, agent & manager notified | Requires processed auto-adjustment + re-sync | 1. Process auto adjustment. 2. Re-sync with claim still open. | Flag + return + notification. | Setup done: 19510788 auto-adjusted and intentionally left NOT posted for the next sync. Re-sync verification pending (next weekly sync). | Not Executed | Next sync
TC-037 | Weekly Re-Sync | §5 | Medium | Claim that now meets closed criteria moves to the relevant Closed queue | Claims 19448701, 19446019, 19445909, 19454954, 19449830, 19449723, 19449752 | 1. Check workflow status of Closed claims. | Claim in Closed queue; recovered amount recognised. | Closed placement correct. 7 Closed claims remain 'Assigned' to agents — acceptable only if intentionally assigned for a special project; confirm. | Partial | OBS-10
TC-038 | Auto Adjustments | §6 | High | Auto-Adjust code list is configurable | Workbench Lists > Auto-Adjust Denial Codes | 1. Open list. | List maintainable; seeded with 242, 197. | 2 active codes: 242, 197; add/deactivate available (admin). | Pass
TC-039 | Auto Adjustments | §6, Feature #8 | High | Process Auto Adjustment: adds system comment, nullifies balance, moves claims to Auto Adjustments queue | Work Queue > Process Automatic Adjustments | 1. Run preview / process on matching claims. | Claims moved to Auto Adjustments (not Completed) with system comment and $0 balance. | Admin selected 19122637 (CO197) → preview '1 non-collectible denial totaling $60.90' → processed; 19510788 (PR242) processed ($228.86). Both moved to Auto Adjustments › System Auto-Adjusted with system comment 'insurance balance … adjusted automatically for denial 197'; RemainingAR = 0, Recovery Status 'No Recovery'. InsuranceBalance field still shows $60.90. | Pass | DEF-20
TC-040 | Auto Adjustments | §6, §10 | High | Admin / Mgr / TL can export the Auto Adjustments queue as a report for bulk PMS posting | Work Queue export | 1. Filter AR Queue = Auto Adjustments. 2. Export. | Dedicated export of Auto Adjustments queue. | Work Queue AR Queue filter offers 'Auto Adjustments · System Auto-Adjusted' (2 claims); Export Filtered returns .xlsx (Admin 9,840 B; Team Lead 200 OK). No dedicated PMS-format report, but export is functional for Admin/TL. | Pass | OBS-11
TC-041 | Financial Fields | §7, Feature #6 | Medium | 'Expected Payment' renamed to 'Revenue Expectation' everywhere | Claim detail; Work Queue grid | 1. Open claim detail. 2. Open Work Queue columns. | Label reads 'Revenue Expectation' in all views. | Claim detail shows 'Revenue Expectation'. Work Queue grid column still titled 'EXPECTED PAYMENT'. | Fail | DEF-10
TC-042 | Financial Fields | §7 | High | Revenue Expectation = Medicare-rate allowable across billed CPTs (0 if no rate) | All claims | 1. Check RevenueExpectation values. 2. Compare with dashboard 'revenue expectation by AR queue'. | Calculated from fee schedule for each claim. | RevenueExpectation = $0.00 on all 84,074 claims ('no fee-schedule rate loaded'). Dashboard 'AR Collections Progress – revenue expectation' instead shows $3,320,502.46 (= Initial Insurance AR). Rate source is open item #5. | Fail | DEF-11
TC-043 | Financial Fields | §7, AT-8 | High | Potential Recovery = Revenue Expectation − (Ins Paid + Pt Paid + Pt Bal), floor 0 | AT-8 case: RevExp $353, Ins paid $120, Pt bal $30 | 1. Locate claim matching case. 2. Check Potential Recovery. | Potential Recovery $203. | Cannot be exercised — Revenue Expectation is $0 on every claim, so Potential Recovery is $0 (dashboard Potential Recovery Amount $0.00). | Blocked | DEF-11
TC-044 | Financial Fields | §7, AT-8 | Medium | Recovery Status: In Progress / Partially Recovered / Fully Recovered / No Recovery | Claim 19448764 (all payments 0) | 1. Open claim Overview. | In Progress when Ins paid, Pt paid and Pt bal are all 0. | Shows 'In Progress' (correct). Partially / Fully Recovered not verifiable while Revenue Expectation = 0. 'No Recovery' definition still open (#6). | Partial | DEF-11
TC-045 | Financial Fields | §7 | High | Recovered Amount = insurance payments dated after denial date; adjustments excluded | Recovery & Financial Analytics | 1. Read metric definition and totals. | Payments only, after denial date. | Analytics definition: 'Recovered is additional payments AND adjustments booked since intake' — adjustments included, basis is intake not denial date. Total Recovered $4,848.94. | Fail | DEF-12
TC-046 | Follow-Up | §8.1 | Medium | Follow-up notes captured at claim level only (no CPT-level notes) | Claim 19448764 > Log Follow-Up Note | 1. Open note form. | Claim-level note only. | Form is claim-level; no CPT selector. | Pass
TC-047 | Follow-Up | §8.1, AT-15 | High | Next Follow-Up Date defaults to today + 45 calendar days | Test date Oct 15, 2026 | 1. Open Log Follow-Up Note. 2. Read default date. | Default = Nov 29, 2026. | Default = 2026-11-29 (setting NextFollowUpDefaultDays = 45). Earlier dates allowed (min = today); later dates NOT blocked (open item #8). Existing notes show agents set 19–31-day dates. | Pass | OBS-12
TC-048 | Attachments | §8.2, Feature #11 | High | Attachments available on follow-up notes for ALL actions | Log Follow-Up Note form | 1. Open form for each Claim Status / Fix-Resolution. 2. Look for file upload. | Upload control on every follow-up note. | No file-upload control in the follow-up form for any status/resolution. Attachments exist only on the client's CIP response (max 3 files). | Fail | DEF-13
TC-049 | Attachments | §8.2 | High | Each upload requires a document category | Document Categories list (6) | 1. Attempt upload. | Category mandatory (Appeal, EOB, Medical Record, Payer Correspondence, CIP Response, Other). | Category list is configured, but no upload UI uses it (client CIP upload has no category). | Fail | DEF-13
TC-050 | Attachments | §8.2 | High | Document Vault: search documents by claim/visit, patient and category | Navigation | 1. Look for Document Vault. | Document Vault screen available. | No Document Vault screen or route in the application. | Fail | DEF-14
TC-051 | Attachments | §8.2 | High | Files stored in Azure Blob with HIPAA controls (encryption at rest, private access, RBAC, audit logging) | Setting DocumentBlobContainer = arwb-documents | 1. Infrastructure review. | Blob storage with HIPAA controls. | Container setting present; storage controls require Azure/infra review — not testable from the UI. | Not Executed | Infra review
TC-052 | Attachments | §8.2, AT-16 | Medium | Uploading a 20 MB file is rejected with a size-limit message | AttachmentMaxBytes = 15,728,640 (15 MB) | 1. Upload 20 MB file. | Rejected with size-limit message. | Client response upload: 16 MB PDF rejected client-side with 'UAT_big_16MB.pdf is larger than 15 MB.'; picker limited to allowed types. Not available on internal follow-ups (DEF-13). | Partial | DEF-13
TC-053 | Write-Off Approval | §8.3, Feature #10 | High | Agent selects Write-Off → claim goes to Submitted for QA | Log Follow-Up Note: Claim Status = Denied | 1. Select Write Off. 2. Save. | Claim routed to QA as a write-off. | ARAgent1 logged 'Write Off' on 19521528 → 'Submitted for QA' (QA KPI 'Write-offs pending review' = 1). | Pass
TC-054 | Write-Off Approval | §8.3, AT-11 | High | QA approves write-off → claim in 'Approved Write-Offs – Pending Posting' in agent's queue with notification; agent marks posted | Requires write-off submission | 1. QA approve. 2. Check agent queue + notification. 3. Mark as Posted. | Pending-posting list + notification 'Write-off approved — perform the write-off in the PMS.' | QA1 approved → claim moved to Auto Adjustments › Approved Write-Offs – Pending Posting; ARAgent1 received notification 'Write-off approved for claim 19521528. Post it in the PMS, then Mark as Posted.' and claim shows in My Work. Agent CANNOT Mark as Posted (no control; API 403 'Only a System Administrator, RCM Manager or Team Lead can assign claims'). TeamLead marked it posted → Closed – Fully Adjusted. | Partial | DEF-17
TC-055 | Escalation / Reassignment | §8.4, Feature #12 | Medium | Escalate to Supervisor with mandatory reason category; routed to TL and AR Manager | Escalation Reasons (6) | 1. As agent, escalate. 2. Check Escalation & Reassignment Requests. | Mandatory reason dropdown + free text; visible to TL and Mgr. | ARAgent1 escalated 19404713: save blocked until reason chosen ('Choose a reason.'); reason 'Payer portal access required' + note. Appeared in Escalation & Reassignment Requests; TeamLead responded and resolved (note required). | Pass
TC-056 | Escalation / Reassignment | §8.4, Feature #12 | Medium | Request Reassignment with mandatory reason category | Reassignment Reasons (5) | 1. As agent, request reassignment. | Mandatory reason dropdown + free text. | ARAgent1 requested reassignment on 19465060 with reason 'Payer call outside my shift'. TeamLead used 'Reassign & Resolve' → ARAgent3; request auto-resolved; audit shows both events. | Pass
TC-057 | Assignment | §8.5, Feature #13 | Medium | Due Date on batch assignment is optional | Assignment Management > Create Assignment Batch | 1. Review batch form. 2. Review existing batch. | Due Date optional; applies to every claim in batch. | Due Date field optional; BATCH-0001 (11 claims) carries due date Oct 23, 2026. | Pass
TC-058 | CIP Workflow | §9.1 | High | Selecting CIP requires internal Follow-Up Comment + client-facing CIP Comment; CIP box only when CIP selected | Log Follow-Up Note; Fix/Resolution = CIP - Client Escalations | 1. Toggle resolution between CIP / non-CIP. | CIP Comment appears only for CIP and is mandatory. | CIP Category*, Required Information* and CIP Comment* appear only when CIP is selected; hidden for Write Off and other resolutions. | Pass
TC-059 | CIP Workflow | §9.1 | High | CIP note goes to Submitted for QA; QA by QA Reviewer / TL / RCM Mgr | Claim 18955927 | 1. Review activity timeline. | Routed to QA; after QA approval enters CIP Pending Approval. | Timeline: routed to QA → 'QA approved the CIP note: the escalation moves to Pending Approval'. | Pass
TC-060 | CIP Workflow | §9.1 | High | CIP Escalations – Pending Approval accessible only to TL, RCM Mgr, Admin; individual or bulk approval | CIP Escalations screen | 1. Open screen. 2. Check roles and bulk actions. | Second approval layer with bulk approve. | Screen roles = admin, manager, lead; 1 case Pending Approval; 'Bulk Approve Selected' and 'Bulk Reject / Send Back Selected' available. | Pass
TC-061 | CIP Workflow | §9.1 | High | Approved CIPs appear in client's Escalation Requests tab | Requires approval + client login | 1. Approve CIP. 2. Log in as client. | CIP visible to scoped client user. | TeamLead bulk-approved CIP-000002 and CIP-000003 ('2 sent to the client'). Both visible to AccountManager (Client Viewer) in Escalation Requests; CIP-000002 visible to Insight Family Practice Clinic Viewer. CIP-000001 (still Pending Approval) hidden from clients. | Pass
TC-062 | CIP Workflow | §9.1, AT-13 | High | Client responds (with attachments) → Client Responded; manager re-escalates or approves → claim returns to original agent | Requires client response | 1. Client responds. 2. Manager approves. | Claim auto-returns to original agent. | AccountManager responded to CIP-000002 with PDF (text mandatory). RCMManager reviewed (response + attachment visible), marked 'Insufficient — Re-send to Client' (reason mandatory) → Round 2 shown to client with feedback. Client responded again with 2nd PDF. RCMManager 'Approve & Return to Agent' → claim back to ARAgent1 (Assigned), both attachments retained by round. | Pass | DEF-19
TC-063 | CIP Workflow | §9.2 | High | Internal follow-up comments and client-facing CIP comments stored and displayed separately; client never sees internal notes | Claim 18955927 | 1. Review stored fields. 2. View as client. | Separate storage; client sees only CIP comment + response. | Stored separately (followUpComment vs cipComment); escalation screens show only the CIP comment. However, Clinic Viewer and Client Viewer can open #/claims/30117 directly: Follow-Ups, Activity Timeline and QA Review tabs show 'UAT-C4 internal…' agent note and QA notes; claim API returns the same. | Fail | DEF-15
TC-064 | Roles & Access | §10 | Medium | Navigation/permissions match the role matrix | App role configuration | 1. Compare each screen's roles with §10 matrix. | Matches matrix. | Verified per role login: Agent (Dashboard, Work Queue, My Work, Follow-Up, Analytics, Reports); QA (Dashboard, QA, Analytics, Reports); TL (+Assignment, CIP, Requests; no Data Processing/Audit/Masters); RCM Mgr (+Data Processing, Status Verification, Audit; no Masters); Client/Clinic Viewer (Dashboard, Escalation Requests, Analytics, Reports). Deviations: Masters admin-only (DEF-08); Agent can't mark write-off posted (DEF-17); QA API data exposure (DEF-16); Analytics/Reports open to Agent/QA (OBS-13). | Partial | DEF-08, DEF-16, DEF-17
TC-065 | User Management | §10.1, Feature #14 | High | Admin creates client users scoped Lab → Clinic with cascading selection | User Management > Add User | 1. Choose role Clinic Viewer. 2. Select lab. | Selecting a lab loads only that lab's clinics. | Roles Client / Clinic / Provider Viewer available; selecting InHealth loads '115 clinics on this lab's claims' for per-lab clinic choice. User not created. | Pass
TC-066 | User Management | §10.1, AT-14 | High | Clinic-scoped user sees only that clinic's data and CIPs; never internal notes | Requires Clinic Viewer login | 1. Log in as clinic user. | Only Clinic A data / CIPs. | Clinic Viewer (Insight Family Practice): escalation list shows only CIP-000002 (not 19490126 / Spark to Recovery); claims, dashboard and queues scoped to 7,300 claims all of this clinic; other-clinic claim → 404. BUT internal notes visible on claim page via direct URL. | Fail | DEF-15
TC-067 | User Management | §10.1 | Medium | CIP escalations for a clinic routed to that clinic's scoped user(s) | Requires Clinic Viewer login | 1. Approve CIP for a clinic. 2. Check scoped user. | Routed to scoped user. | CIP-000002 routed to the Insight Family Practice Clinic Viewer (visible), but Clinic Viewer is read-only ('the client contact responds') — no Respond action. Only the lab-level Client Viewer could respond. | Partial | DEF-18
TC-068 | Export / Import | Project instructions | Medium | AR users can export claims to Excel and update status via Excel upload | Work Queue toolbar | 1. Review export / bulk update options. | Export and bulk update available. | Export Filtered / Export All / Bulk Update (Excel) present for Admin, TL, Agent; Auto-Adjust export verified (.xlsx). Client Viewer has no claim export (Work Queue blocked) — requirement says client can export line items. Bulk upload not executed. | Partial | OBS-14

## Role Workflow Tests
Step ID | Role | Login | Scenario / Requirement | Claim(s) | Action Performed | Expected Result | Actual Result | Status | Defect Ref
RW-01 | System Administrator | ARWBInhealthSA | Assign claims with optional due date (§8.5) | 19538684 + 6 others | Work Queue › search › select › Assign Selected → ARAgent1, due 20-Oct, note | Claims assigned; due date optional | '1 assigned — ARAgent1.'; other 6 assigned via same service; status Assigned | Pass
RW-02 | System Administrator | ARWBInhealthSA | Process Automatic Adjustment on selected claims (§6) | 19122637, 19510788 | Select claim › Process Automatic Adjustments › confirm | Only selected claims adjusted; moved to Auto Adjustments with system comment | Preview showed only the selected claim ($60.90); processed → Auto Adjustments › System Auto-Adjusted; system comment added; RemainingAR 0; InsuranceBalance field unchanged | Pass | DEF-20
RW-03 | System Administrator | ARWBInhealthSA | Export Auto Adjustments queue (§6) | — | AR Queue filter = Auto Adjustments › Export Filtered | Excel report of the queue | 2 claims listed; .xlsx returned | Pass | OBS-11
RW-04 | AR Agent | ARAgent1 | Agent sees only own work; restricted queues hidden (§3.2, §10) | — | Open Work Queue; probe NC/Closed queues, other claim, assign & QA endpoints | Own claims only; no assign/QA | 18 own claims; NC/Closed = 0; other claim 404; assign 403; QA 403; no Assign / Auto-Adjust buttons | Pass
RW-05 | AR Agent | ARAgent1 | Log follow-up → Submitted for QA (§8.1) | 19144266 | Claim Status Denied, Fix 'Appealed', comment; default next date | Routed to QA; next date = today + 45 | 'sent to the QA Verification Queue'; Next follow-up 29-Nov-2026 | Pass
RW-06 | AR Agent | ARAgent1 | Write-off submission (§8.3) | 19521528 | Fix 'Write Off' › Save | Submitted for QA as write-off | Submitted for QA; QA KPI 'Write-offs pending review' = 1 | Pass
RW-07 | AR Agent | ARAgent1 | CIP escalation with mandatory CIP comment (§9.1) | 19524452, 19490126 | Fix 'CIP - Client Escalations'; save without CIP comment, then with | Blocked without CIP comment; then routed to QA | 'Add the CIP comment the client will see.'; after entry → Submitted for QA | Pass
RW-08 | AR Agent | ARAgent1 | Escalate to Supervisor with mandatory reason (§8.4) | 19404713 | Escalate without reason, then with 'Payer portal access required' | Reason mandatory; request raised | 'Choose a reason.'; then 'escalated to a supervisor' | Pass
RW-09 | AR Agent | ARAgent1 | Request Reassignment with reason (§8.4) | 19465060 | Reason 'Payer call outside my shift' + note | Request raised; claim stays with agent | 'Reassignment requested… stays with you until a lead reassigns it.' | Pass
RW-10 | QA Reviewer | QA1 | QA reject → back to same agent (§3.2) | 19538684 | Reject: Error Type 'Incomplete Documentation', scoring, note | QA Rejected, assigned to ARAgent1 | 'returned to the same agent under QA Rejected'; AssignedAgent ARAgent1 | Pass
RW-11 | QA Reviewer | QA1 | QA approve normal / write-off / CIP (§8.3, §9.1) | 19144266, 19521528, 19524452, 19490126 | Approve each | Completed / Approved Write-Offs Pending Posting / CIP Pending Approval | 19144266 Completed; 19521528 → Approved Write-Offs – Pending Posting; both CIPs → Pending Approval | Pass
RW-12 | QA Reviewer | QA1 | QA role limits (§10) | — | Open Work Queue page; probe assign/CIP/masters/claims APIs | No work-queue / restricted data | UI: 'cannot open Work Queue'; assign/CIP/masters 403; BUT claims API returns 84,074 incl. 749 NC | Partial | DEF-16
RW-13 | AR Agent | ARAgent1 | Write-off approval notification & posting (§8.3, AT-11) | 19521528 | Check notifications/My Work; try Mark as Posted | Notification + pending-posting item; agent marks posted | Notification received; item in My Work; Mark as Posted not available (403) | Partial | DEF-17
RW-14 | AR Agent | ARAgent1 | Rework QA-rejected claim | 19538684 | View QA Review tab; log corrected follow-up | QA feedback visible; resubmitted | Error type, notes and scoring visible; resubmitted to QA | Pass
RW-15 | Team Lead | TeamLead | Bulk QA approve (§9.1 QA by TL) | 19538684 | QA › select › Approve Selected | Approved; self-work guard | '1 approved.'; dialog notes own-work claims skipped | Pass
RW-16 | Team Lead | TeamLead | Bulk CIP second approval (§9.1) | 19524452, 19490126 | CIP Escalations › select both › Bulk Approve | Sent to client | '2 sent to the client.' Status Sent to Client | Pass
RW-17 | Team Lead | TeamLead | Respond to escalation; reassign on request (§8.4) | 19404713, 19465060 | Respond › Mark Resolved; Reassign & Resolve → ARAgent3 | Escalation resolved; claim reassigned, request closed | Both resolved; audit 'Reassigned from ARAgent1 to ARAgent3' | Pass
RW-18 | Team Lead | TeamLead | Mark write-off / auto-adjustment as posted (§6, §8.3) | 19521528, 19122637 | Select › Mark as Posted | Posted; claim closes | '1 claim(s) marked as posted'; 19521528 → Closed – Fully Adjusted | Pass
RW-19 | Team Lead | TeamLead | Restricted queue visibility; masters access (§3.2, §10) | — | Query NC/Closed; open Master Values | Sees restricted queues; cannot maintain lists | NC 749 / Closed 21,090 visible; masters 403 | Pass
RW-20 | Clinic Viewer | ClinicViewer (Insight Family Practice) | Clinic scope & CIP routing (§10.1, AT-14) | 19524452 vs 19490126 | Open Escalation Requests; probe other-clinic claim | Only own clinic data and CIPs | Only CIP-000002; 7,300 claims all Insight Family Practice; other clinic claim 404 | Pass
RW-21 | Clinic Viewer | ClinicViewer (Insight Family Practice) | Client never sees internal notes (§9.2) | 19524452 | Open #/claims/30117 directly; Follow-Ups / Activity / QA tabs | Internal notes hidden | Internal agent note and QA notes visible | Fail | DEF-15
RW-22 | Clinic Viewer | ClinicViewer (Insight Family Practice) | Clinic user responds to CIP (§9.1, §10.1) | 19524452 | Open request | Respond with info/attachments | Read-only: 'the client contact responds'; no Respond | Fail | DEF-18
RW-23 | Client Viewer | AccountManager | Client responds with attachment; size limit (§9.1, AT-16) | 19524452 | Attach 16 MB file; submit empty; submit text + PDF | 16 MB rejected; text required; response accepted | 'larger than 15 MB'; 'Enter the requested information.'; 'Response submitted… with 1 attachment(s)' | Pass
RW-24 | Client Viewer | AccountManager | Client never sees internal notes (§9.2) | 19524452 | Claim API / page | Hidden | Internal notes returned | Fail | DEF-15
RW-25 | RCM Manager | RCMManager | Review client response → insufficient → re-escalate (§9.1) | 19524452 | Review Response › Insufficient (no note, then note) | Note mandatory; client gets round 2 with feedback | 'Add a reason first.'; re-sent; client sees Round 2 + 'Needs more info' feedback | Pass | DEF-19
RW-26 | RCM Manager | RCMManager | Reassign claim (§10) | 19404713 | Assign → ARAgent3 with due date | Reassigned | '1 reassigned — ARAgent3.'; audit entry | Pass
RW-27 | RCM Manager | RCMManager | Maintain NC / Auto-Adjust lists (§10) | — | Open Workbench Lists | Allowed | 'cannot open Workbench Lists'; API 403 | Fail | DEF-08
RW-28 | RCM Manager | RCMManager | Audit trail & progress monitoring (§10, project scope) | — | Audit Logs; Dashboard Agent Productivity | All actions logged; progress by agent | 244 audit entries incl. every UAT action; ARAgent1 16 assigned / 6 completed | Pass
RW-29 | Client Viewer | AccountManager | Second-round response (§9.1) | 19524452 | Respond again with signed requisition PDF | Accepted | 'Response submitted… 1 attachment(s)' | Pass
RW-30 | RCM Manager | RCMManager | Approve client response → returns to original agent (§9.1, AT-13) | 19524452 | Review Response › Approve & Return to Agent | Claim auto-returns to ARAgent1 | 'response approved - the claim is back with the AR agent'; Assigned to ARAgent1; queue CIP Response Received; both attachments retained | Pass

## Defect Log
Defect ID | Linked Test Case(s) | Area | Severity | Description | Status
DEF-01 | TC-004 | Dashboard | High | Dashboard insights panel does not show the current week's uploaded Key Observations; shows system-generated top-5 list instead (216, 252, 31, 27, 96) while Data Processing current week shows only CO-216. | Open
DEF-02 | TC-004, TC-005 | Dashboard / Data Processing | Medium | Denial code Description shows '—' on Dashboard and on system-generated insight rows although the Denial Code Master holds descriptions (e.g., 216). | Deferred
DEF-03 | TC-009 | Claim Detail > Denial Info | Medium | Denial Reason and 'All Denial Codes' empty for claim with curated 'CO11, CO252'; 'Line-Level Codes' renders '11252' (codes concatenated without separator). | Open
DEF-04 | TC-010 | Claim Detail > CPT / Line Detail | Low | No per-CPT expand control; line denial sub-row lacks description and classification (only on Denial Info tab). | Open
DEF-05 | TC-021 | Work Queue feed | High | Work-queue feed / nav badge (9,054) includes Non-Collectible (759) and Unbilled (1,102) claims; spec limits auto-feed to the 4 Possible Collectible queues (7,193). | Open
DEF-06 | TC-021 | Dashboard KPI | High | 'Claims Awaiting Assignment' (83,986) counts every unassigned claim incl. Closed and Patient AR; should count only open Possible Collectible claims. | Open
DEF-07 | TC-022 | Configuration | High | Two conflicting Non-Collectible sources: Workbench list (197, 242, 257, 288, 27, 31) vs Denial Code Master flags (29, 119, 193, 197, 204, 242, 243, 279). Queue engine uses Workbench list; 204/29 etc. treated as collectible. | Open
DEF-08 | TC-023, TC-064 | Roles & Access | Medium | RCM Manager cannot maintain NC / Auto-Adjust lists — Master Values is admin-only. | Open
DEF-09 | TC-031 | Denial categorization | High | 50 primary denial codes unmapped (incl. 216 – 1,708 claims / $594.6K); 48% of denied claims categorised 'Other'. Dependent on open item #2. | Deferred
DEF-10 | TC-041 | Work Queue grid | Low | Column header still 'Expected Payment'; should read 'Revenue Expectation'. | Open
DEF-11 | TC-042, TC-043, TC-044 | Financial fields | High | Revenue Expectation = $0 on all claims (no fee schedule loaded) so Potential Recovery / Recovery Status cannot work; dashboard 'revenue expectation' uses Initial Insurance AR instead. Dependent on open item #5. | Open – dependency
DEF-12 | TC-045 | Analytics | High | Recovered Amount definition includes adjustments and measures from intake; spec = insurance payments only, dated after denial date. | Open
DEF-13 | TC-048, TC-049, TC-052 | Attachments | High | No attachment upload on follow-up notes; no mandatory document category on uploads. | Open
DEF-14 | TC-050 | Document Vault | High | Document Vault (search by claim/visit, patient, category) not implemented. | Open
DEF-15 | TC-063, TC-066 | Security / Comment visibility | Critical | Client users (Clinic Viewer and Client Viewer) can open the full claim page via direct URL (#/claims/{key}) and the claim API; Follow-Ups, Activity Timeline and QA Review expose internal agent notes and QA notes (e.g., claim 19524452). Violates §9.2. | Open
DEF-16 | TC-016, TC-024 | Security / Access | Medium | QA Reviewer: Work Queue page blocked in UI, but claims/queues API returns all 84,074 claims including restricted Non-Collectible and Closed queues. Enforce role scope server-side. | Open
DEF-17 | TC-054 | Write-off posting | High | AR Agent cannot 'Mark as Posted' an approved write-off (no control; API 403 with misleading message 'Only … can assign claims'). §8.3 says the agent posts in PMS and marks the claim complete. | Open
DEF-18 | TC-067 | CIP / Client users | Medium | Clinic Viewer is read-only and cannot respond to CIPs routed to their clinic; only the lab-level Client Viewer can respond. Conflicts with §9.1/§10.1 (CIPs routed to clinic-scoped users who respond). Confirm intended design. | Open – clarify
DEF-19 | TC-062 | AR Queue | Low | After the client responds, claim remains in 'Client Escalation (CIP) Pending'; it only enters 'CIP Response Received' after the manager approves and returns it to the agent. §3.1 defines CIP Response Received as 'client has responded'. | Open
DEF-20 | TC-039 | Auto Adjustments | Low | After auto-adjustment, RemainingAR = 0 but claim InsuranceBalance still shows the original amount (19122637: $60.90). §6 says nullify the balance within the Workbench. | Open

## Observations
Obs ID | Linked Test Case(s) | Observation / Clarification Needed
OBS-01 | TC-001 | Data Processing header 'Master File Loaded' shows '—' even though run #3 loaded a file.
OBS-02 | TC-006 | Insight count (1,699) uses primary denial only; routed Work Queue filter returns 1,700 (includes a claim with 216 as secondary code). Align filter with insight basis.
OBS-03 | TC-014 | 2 Non-Responder claims have source status 'Patient Responsibility' — confirm intended.
OBS-04 | TC-015 | 100 Denied – Possible Collectible claims carry an NC/terminal code (e.g., 242) as a secondary code in the curated column; will move once Phase 2 hierarchy is delivered.
OBS-05 | TC-019 | No Patient AR claim retains a denial code, so 'denial present → still Patient AR' could not be exercised.
OBS-06 | TC-020, TC-033 | Extra queues not in spec: 'Unbilled (Not Yet Billed)' and 'Status Change Verification'. Confirm with business owner and add to the requirement doc.
OBS-07 | TC-025 | Claims API returns AssignedAgentName = null while AssignedAgentUser is populated (display name gap).
OBS-08 | TC-029 | 'CR' (Corrections & Reversals) group prefix not stripped — CR96 falls to Unmapped/'Other'. Spec lists CO/PR/PI/OA only; confirm whether CR should be added.
OBS-09 | TC-035 | Assignment page '6,066 claims untouched for 45+ days' counts never-worked claims; ensure this is not confused with the Re-Follow-Up – Unresolved rule (touched claims only).
OBS-10 | TC-037 | 7 Closed claims remain 'Assigned' — confirm they were assigned intentionally (special project) rather than left assigned after closing on sync.
OBS-11 | TC-040 | No dedicated 'Export Auto Adjustments report' for PMS posting; relies on generic export.
OBS-12 | TC-047 | Later-than-45-day next follow-up dates are not blocked (open item #8).
OBS-13 | TC-064 | Analytics & Reports visible to AR Agent and QA Reviewer; matrix leaves these blank — confirm intended.
OBS-14 | TC-068 | Client Viewer has no claim/line-item export (Work Queue blocked); project instructions say Account Manager / Client can export denial line items to Excel — confirm whether Reports exports cover this.
OBS-15 | RW (all) | 1,165 unassigned Possible Collectible claims have no clinic on the claim, so clinic-scoped users will never see them; confirm clinic mapping in the master file.

## Mockup Comparison
Ref | Area | Mockup (Demo Account HTML) | Application (Test) | Assessment
M-01 | Navigation / screens | 16 screens incl. My Work, System Settings, Client Escalation Requests (viewer) | All screens present; 'System Settings' replaced by 'Master Values' (9 sub-pages); adds 'Status Change Verification' | Aligned (with additions)
M-02 | Personas / roles | Admin, RCM Manager, Team Lead, AR Agent, QA Reviewer, Client Viewer (client / clinic / provider scopes) | Same 8 roles incl. Clinic Viewer and Provider Viewer | Aligned
M-03 | Dashboard KPI tiles | 10 tiles: Eligible Claims, Outstanding Ins AR, Awaiting Assignment, In Progress, Awaiting QA, QA Rejected, Completed/Closed, Recovered, Potential Recovery, Overdue Follow-Ups | Same 10 tiles | Aligned (values: see DEF-06, DEF-11)
M-04 | Dashboard insight table | Denial code, description, counts, balance, top payer, impact, observation, category, action | Same columns; descriptions blank | Partially aligned (DEF-02)
M-05 | Work Queue filters | Client, payer, panel, category, status, agent, priority, aging, AR queue, TFL, search, saved views | Same plus Clinic, Open Ins AR only, Non-collectible only | Aligned
M-06 | Work Queue column | 'Expected Payment' | 'Expected Payment' (mockup pre-dates handoff rename) | Both outdated vs handoff (DEF-10)
M-07 | Claim detail financials | Expected Payment, Potential Recovery | Revenue Expectation, Potential Recovery, Recovery Status | App follows handoff (better than mockup)
M-08 | Process Automatic Adjustments | Button in restricted Work Queue; claims moved to Completed | Button present; Auto Adjustments queue created (per handoff) | App follows handoff
M-09 | Log Follow-Up Note | Claim Type, Follow-Up Type, Claim Status, Root Cause, Fix/Resolution, Comment, Next Follow-Up | Same fields + CIP Category / Required Info / CIP Comment | Aligned; neither has attachments (DEF-13)
M-10 | CIP Escalations | Review, bulk approve / reject, return to agent, re-escalate | Same lifecycle and bulk actions | Aligned
M-11 | Escalation & Reassignment Requests | Screen for Admin/Mgr/TL with Mark Resolved | Same; reassigning resolves request | Aligned
M-12 | Reports | Denial Analysis, Panel Type, AR Aging, Recovery Performance, Agent Productivity | Same 5 plus Recovery Trend, Action Completion, Operational SLA, AR Collections Progress; RPT-01–09 map | Aligned (extended)
M-13 | Assignment Management | Batch by category with Due Date; untouched claims list | Same | Aligned
M-14 | Non-Collectible list | System Settings (admin only) | Master Values > Workbench Lists (admin only) | Both conflict with handoff role matrix (DEF-08)
M-15 | Document Vault | Not in mockup | Not built | Gap vs handoff (DEF-14)

## Queue Reconciliation
Queue reconciliation – all 84,074 claims (API pull, 15 Oct 2026)
Queue | Sub-queue | Claims | Unassigned | Auto-fed per spec? | Rule exceptions found
Closed | Fully Paid | 42502 | 42502 | No | 0
Closed | Fully Adjusted | 21088 | 21081 | No | 0
Patient AR | — | 11349 | 11349 | No | 0
Non-Responder | Possible Collectible | 2627 | 2622 | Yes | 0
Denied | Possible Collectible | 4280 | 4220 | Yes | 0
Denied | Non-Collectible | 751 | 751 | No | 0
Partially Paid | Possible Collectible | 302 | 290 | Yes | 0
Partially Paid | Non-Collectible | 8 | 8 | No | 0
Partially Adjusted | Possible Collectible | 61 | 61 | Yes | 0
Unbilled (not in spec) | — | 1102 | 1102 | Not defined | 0
QA Rejected | — | 1 | 0 | — | 0
Client Escalation (CIP) Pending | — | 1 | 0 | — | 0
Completed Claims | — | 2 | 0 | — | 0
Total |  | 84074 | 83986
Unassigned in spec auto-fed queues |  |  | 7193
Work Queue nav badge (observed in app) |  |  | 9054
Variance (badge − spec) |  |  | 1861
Dashboard 'Claims Awaiting Assignment' (observed) |  |  | 83986
Blue values were read from the app UI on 15 Oct 2026; counts in the table come from the claims API pull.