## Summary
LRN Report Snapshots - Parquet Storage: Implementation Plan
Source: docs/LRN_Report_Snapshots–Parquet_Storage_Implementation.pdf (20 Oct 2026). Est. days are planning estimates (assumption), not from the doc.
Phase | Phase Name | Goal | Tasks | Est. Days | Done | In Progress | Blocked | % Done
P0 | Preparation & decisions | Lock scope: which reports/result sets are snapshotted, at what grain, and where the code lives.
P1 | Infrastructure & LRNMaster schema | Blob container, identity/network/retention controls and the snapshot index tables + SPs.
P2 | LRN.Snapshots shared library | Writer, validator, blob store, index repository, cache and DuckDB reader shared by worker and web app.
P3 | Worker write path | LRN.MasterFileProcessorWorker writes, validates, uploads and registers snapshots after each successful weekly run; retention.
P4 | Dashboard read path | IReportDataSource abstraction with SQL and Parquet implementations, snapshot catalog, cache and lab isolation.
P5 | Pilot reports UI (2-3 reports) | Mapper refactor, filter parity, week selector, read-only banner and export label for the pilot reports.
P6 | Testing | Unit, integration and parity tests from the design-doc test checklist.
P7 | Pilot rollout & UAT | One pilot lab in production, client UAT on real past weeks.
P8 | Remaining reports & all labs | Extend to every standard report with filter parity, then enable all labs.
P9 | Backfill, monitoring & handover | Optional backfill of past weeks, monitoring, developer docs.
Total
How to use
• Fill in the yellow cells on 'Task Split' (Owner, Start Date, End Date, Status, Notes). Status is a dropdown: Not Started / In Progress / Blocked / Done.
• Blue numbers in 'Est. Days' are editable estimates; this summary recalculates from them.
• Rows turn green when Done, blue when In Progress, red when Blocked.
• Critical path: P0 -> P1 -> P2 -> P3 (write) and P4 (read) in parallel -> P5 -> P6 -> P7 -> P8 -> P9.

## Task Split
Task ID | Phase | Phase Name | Task | Details | Project / Area | Deliverable | Depends On | Est. Days | Doc Page(s) | Owner | Start Date | End Date | Status | Notes
P0-01 | P0 |  | Confirm report & result-set inventory | List every standard report (ReportCode), its SP, and each result set name to snapshot. Mark which reports are in the pilot. | Analysis | Report inventory sheet signed off |  | 1.5 | 1, 5 |  |  |  | Not Started
P0-02 | P0 |  | Define snapshot grain per report | For each result set confirm it is stored at the grain the UI filters/pages on (payer, clinic, month), not pre-filtered by a user selection. Identify SPs that need a 'no user filter' mode. | Analysis | Grain decision per result set | P0-01 | 1.5 | 3 |  |  |  | Not Started
P0-03 | P0 |  | Decide code location for writer | Doc says LRN.Snapshots is referenced by 'LRN.ReportEngine', which does not exist in this repo. Confirm it is referenced by LRN.MasterFileProcessorWorker (or LRN.ReportWorker). | Architecture | Decision recorded |  | 0.5 | 5 |  |  |  | Not Started
P0-04 | P0 |  | Review existing blob code for reuse | Check LRN.AzBlobSync / LRN.DataLibrary for existing BlobContainerClient + DefaultAzureCredential setup to reuse. | Architecture | Reuse notes |  | 0.5 | 5 |  |  |  | Not Started
P0-05 | P0 |  | Define configuration contract | Options: container name, cacheRoot, RowGroupSize (100,000), Compression (Snappy/Zstd per report), KeepWeekly=5, KeepMonthEnd=5, cache max idle=7 days, per-report SchemaVersion. | Architecture | appsettings schema + options classes spec | P0-01 | 0.5 | 4, 5, 18 |  |  |  | Not Started
P1-01 | P1 |  | Create ReportSnapshotRun table | LRNMaster: SnapshotRunId, LabId, LabName, RunId, WeekFolder, SnapshotDate, Status (InProgress¦Success¦Failed), ErrorMessage, CreatedOn, CompletedOn; UQ (LabId, RunId). | Database/LRNMaster | Migration script | P0-05 | 0.5 | 10 |  |  |  | Not Started
P1-02 | P1 |  | Create ReportSnapshotFile table | FK to run ON DELETE CASCADE; ReportCode, ResultSetName, BlobPath, RowCount, SizeBytes, ContentSha256, SchemaJson, SchemaVersion; UQ (SnapshotRunId, ReportCode, ResultSetName). | Database/LRNMaster | Migration script | P1-01 | 0.5 | 10 |  |  |  | Not Started
P1-03 | P1 |  | Write index stored procedures | Upsert run (InProgress -> Success/Failed), upsert file row (idempotent on re-run), usp_ReportSnapshot_List @LabId,@ReportCode (Success only, newest first), file lookup by SnapshotRunId+ReportCode+ResultSetName+LabId. | Database/LRNMaster | SPs + grants | P1-02 | 1.5 | 10, 11, 17 |  |  |  | Not Started
P1-04 | P1 |  | Write usp_ReportSnapshot_GetExpired | @LabId, @KeepWeekly=5, @KeepMonthEnd=5: keep a run if it is one of the 5 latest, or the latest run of one of the 5 latest months; return everything else. | Database/LRNMaster | SP + test script | P1-01 | 1 | 18 |  |  |  | Not Started
P1-05 | P1 |  | Create Blob container report-snapshots | Private container (no public access) in the storage account; blob soft delete 7-14 days. | Azure | Container provisioned |  | 0.5 | 3, 18 |  |  |  | Not Started
P1-06 | P1 |  | Configure managed identities & RBAC | Worker = Storage Blob Data Contributor, web app = Storage Blob Data Reader, via DefaultAzureCredential. | Azure | Role assignments | P1-05 | 0.5 | 18 |  |  |  | Not Started
P1-07 | P1 |  | Network & encryption controls | Private endpoint or storage firewall limited to the VM/VNet; confirm at-rest encryption (CMK if compliance requires). | Azure | Network rule / endpoint | P1-05 | 1 | 18 |  |  |  | Not Started
P1-08 | P1 |  | Lifecycle management rule | Safety net: move to Cool after 45 days, delete after 200 days. Never Archive tier. | Azure | Lifecycle policy | P1-05 | 0.25 | 19 |  |  |  | Not Started
P1-09 | P1 |  | Web cache folder & ACL | Create the local cache folder on the web server with restricted ACL (PHI). | Infra/Web server | Folder + ACL |  | 0.25 | 19 |  |  |  | Not Started
P2-01 | P2 |  | Create LRN.Snapshots class library | New project; add Parquet.Net, DuckDB.NET.Data.Full, Azure.Storage.Blobs, Azure.Identity, Microsoft.Data.SqlClient. Add to solution. | LRN.Snapshots | Project skeleton | P0-03 | 0.5 | 5 |  |  |  | Not Started
P2-02 | P2 |  | Options & blob path builder | SnapshotOptions binding; deterministic path {labCode}/{yyyy}/{weekFolder}/{runId}/{reportCode}/{resultSetName}.v{schemaVersion}.parquet. | LRN.Snapshots | SnapshotOptions, BlobPathBuilder | P2-01, P0-05 | 0.5 | 3 |  |  |  | Not Started
P2-03 | P2 |  | ParquetSnapshotWriter | DbDataReader -> Parquet: schema from GetColumnSchema(), unique names (Col{n}, _1/_2), 100,000-row groups, typed buffers, empty report still writes a valid file, returns RowCount + SchemaJson. | LRN.Snapshots | ParquetSnapshotWriter.cs | P2-01 | 2 | 6-9 |  |  |  | Not Started
P2-04 | P2 |  | SQL -> Parquet type mapping | Implement mapping table: ints nullable, decimal(p,s) from schema (money -> 19,4), float/real, bit, date/datetime -> TIMESTAMP, datetimeoffset -> UTC, strings UTF8, Guid/sql_variant -> string, varbinary. | LRN.Snapshots | Map() + unit tests | P2-03 | 1 | 4, 8 |  |  |  | Not Started
P2-05 | P2 |  | DuckDB row-count validator | SELECT COUNT(*) FROM read_parquet(path) must equal rows written; throw on mismatch. | LRN.Snapshots | SnapshotValidator | P2-03 | 0.5 | 9 |  |  |  | Not Started
P2-06 | P2 |  | Blob snapshot store | SHA-256 hash, upload with overwrite, ContentType application/vnd.apache.parquet, metadata sha256; delete blobs for retention; download for cache. | LRN.Snapshots | BlobSnapshotStore | P2-02 | 1 | 3, 9 |  |  |  | Not Started
P2-07 | P2 |  | Snapshot index repository | ISnapshotIndex: StartRun, AddFileAsync(SnapshotFileInfo), CompleteRun/FailRun, ListAsync (catalog), GetFile (with LabId check), GetExpired, DeleteRun. | LRN.Snapshots | SqlSnapshotIndex | P1-03, P1-04 | 1.5 | 9, 10, 17, 18 |  |  |  | Not Started
P2-08 | P2 |  | SnapshotFileCache | Cache by {cacheRoot}/{sha256}.parquet, per-file SemaphoreSlim, download to .part then move, touch LastAccessTime, Purge(maxIdle). | LRN.Snapshots | SnapshotFileCache | P2-06 | 1 | 11-12 |  |  |  | Not Started
P2-09 | P2 |  | ParquetReportReader (QueryAsync + CountAsync) | In-memory DuckDB; column whitelist via DESCRIBE; parameterised filter values; quoted identifiers; ORDER BY only on known column; LIMIT/OFFSET paging; CountAsync with same WHERE. | LRN.Snapshots | ParquetReportReader | P2-01 | 1.5 | 12-13 |  |  |  | Not Started
P2-10 | P2 |  | Extend ReportQuery for range / IN filters | Doc's reader only does equality. Add date-range and IN-list filter types so live SP filters can be mirrored. | LRN.Snapshots | Filter model + WHERE builder | P2-09 | 1 | 14 |  |  |  | Not Started
P2-11 | P2 |  | Unit tests for LRN.Snapshots | Round-trip write/read per SQL type, decimals precision/scale, NULLs, empty file, duplicate column names, injection-safe filter/sort. | tests | LRN.Snapshots.Tests | P2-03..P2-10 | 2 | 19 |  |  |  | Not Started
P3-01 | P3 |  | Report snapshot definitions config | Per report: ReportCode, SP name, parameters, result set names, SchemaVersion, compression override, enabled flag, pilot labs list. | LRN.MasterFileProcessorWorker | Config + ReportSnapshotDefinition | P0-01, P2-02 | 0.5 | 5 |  |  |  | Not Started
P3-02 | P3 |  | Snapshot orchestrator service | After a lab's weekly run is marked Success: start run (InProgress), execute each SP with CommandBehavior.SequentialAccess, write each result set to a temp file, validate, upload, register, mark Success. | LRN.MasterFileProcessorWorker | ReportSnapshotService | P3-01, P2-03..P2-07 | 2 | 5, 9 |  |  |  | Not Started
P3-03 | P3 |  | Hook into weekly run completion | Call the orchestrator at the point the weekly run is marked Success; must not block or fail the weekly load. | LRN.MasterFileProcessorWorker | Integration point | P3-02 | 1 | 5, 10 |  |  |  | Not Started
P3-04 | P3 |  | Failure isolation & retry | Catch all snapshot errors: Status=Failed, ErrorMessage, write LRN_Error_Log; retry failed/missing runs next cycle. | LRN.MasterFileProcessorWorker | Error handling + retry | P3-02 | 1 | 10 |  |  |  | Not Started
P3-05 | P3 |  | Idempotent re-run | Re-running same RunId overwrites blobs and upserts file rows (no duplicates). | LRN.MasterFileProcessorWorker | Upsert logic | P3-02, P1-03 | 0.5 | 3, 19 |  |  |  | Not Started
P3-06 | P3 |  | Retention job | After each successful snapshot: GetExpired -> delete blobs first -> delete ReportSnapshotRun (files cascade). Counts from config. | LRN.MasterFileProcessorWorker | RetentionService | P1-04, P2-06, P2-07 | 1 | 18 |  |  |  | Not Started
P3-07 | P3 |  | Temp file cleanup, logging & metrics | Delete local temp parquet after upload; log per-file rows, size, duration; snapshot run duration. | LRN.MasterFileProcessorWorker | Logging | P3-02 | 0.5 | 20 |  |  |  | Not Started
P3-08 | P3 |  | DI registration & appsettings | Register LRN.Snapshots services, BlobContainerClient via DefaultAzureCredential, options. | LRN.MasterFileProcessorWorker | Program.cs + appsettings | P3-02 | 0.5 | 18 |  |  |  | Not Started
P4-01 | P4 |  | IReportDataSource abstraction | ReadAsync<T>(ReportQuery, map), CountAsync(ReportQuery), IsSnapshot, SnapshotLabel. | LabMetricsDashboard | Interface | P2-09 | 0.5 | 14 |  |  |  | Not Started
P4-02 | P4 |  | SqlReportDataSource (live) | Wraps existing SP calls (SqlDataReader passed as DbDataReader) for the live path. | LabMetricsDashboard | Implementation | P4-01 | 1 | 14-15 |  |  |  | Not Started
P4-03 | P4 |  | ParquetReportDataSource (snapshot) | Resolve file via index (LabId check) -> cache -> ParquetReportReader. Label 'Week_41 (as of 12-Oct-2026)'. | LabMetricsDashboard | Implementation | P4-01, P2-08, P2-09 | 1 | 11, 15-16 |  |  |  | Not Started
P4-04 | P4 |  | Data source factory & snapshot catalog | _live.Create(connString) / _snapshots.Create(labId, snapshotRunId); _catalog.ListAsync(labId, reportCode) using usp_ReportSnapshot_List. | LabMetricsDashboard | Factory + catalog service | P4-02, P4-03 | 0.5 | 15-17 |  |  |  | Not Started
P4-05 | P4 |  | Lab isolation & 404 handling | Snapshot id belonging to another lab (or missing) returns 404. | LabMetricsDashboard | Guard + tests | P4-03 | 0.5 | 11, 19 |  |  |  | Not Started
P4-06 | P4 |  | Cache purge hosted service | Daily BackgroundService calling SnapshotFileCache.Purge(7 days). | LabMetricsDashboard | Hosted service | P2-08 | 0.5 | 12, 19 |  |  |  | Not Started
P4-07 | P4 |  | DI & appsettings for web app | Register LRN.Snapshots read services, reader-role BlobContainerClient, cacheRoot. | LabMetricsDashboard | Program.cs + appsettings | P4-04 | 0.5 | 18 |  |  |  | Not Started
P5-01 | P5 |  | Refactor pilot mappers to DbDataReader | Change pilot mappers' parameter to DbDataReader; read numbers with Convert.*; tolerate missing columns (HasColumn). | LabMetricsDashboard | Mappers (pilot reports) | P4-01 | 1.5 | 14, 19 |  |  |  | Not Started
P5-02 | P5 |  | Filter parity for pilot reports | Mirror each pilot SP's filters (date ranges, IN-lists) in the Parquet WHERE builder. | LabMetricsDashboard | Per-report filter mapping | P2-10, P5-01 | 2 | 14 |  |  |  | Not Started
P5-03 | P5 |  | Controller changes for pilot reports | Add snapshot param; choose source by snapshot null/not-null; populate IsSnapshot, SnapshotLabel, SelectedSnapshotRunId, Snapshots. | LabMetricsDashboard | Controllers | P4-04, P5-01 | 1.5 | 15-16 |  |  |  | Not Started
P5-04 | P5 |  | ISnapshotAwareViewModel | Common interface for LabKey, IsSnapshot, SnapshotLabel, SelectedSnapshotRunId, Snapshots; implement on pilot view models. | LabMetricsDashboard | Interface + VMs | P5-03 | 0.5 | 16 |  |  |  | Not Started
P5-05 | P5 |  | _SnapshotSelector partial & banner | 'Data as of' dropdown (Current (live) + snapshots), read-only warning banner with 'Back to current'. Optionally drop current week from list. | LabMetricsDashboard | _SnapshotSelector.cshtml | P5-04 | 1 | 16-17 |  |  |  | Not Started
P5-06 | P5 |  | Disable write actions in snapshot mode | Hide/disable assign, status change, notes when IsSnapshot. | LabMetricsDashboard | View changes | P5-05 | 0.5 | 17 |  |  |  | Not Started
P5-07 | P5 |  | Paging/sorting & DataTables server-side | Confirm server-side paging/sorting re-queries the Parquet file; pager totals from CountAsync. | LabMetricsDashboard | Verified grids | P5-03 | 0.5 | 17 |  |  |  | Not Started
P5-08 | P5 |  | Excel/PDF export snapshot label | Exports use same VM; add snapshot label to export header. | LabMetricsDashboard | Export changes | P5-03 | 0.5 | 17 |  |  |  | Not Started
P6-01 | P6 |  | Worker integration test (pilot lab) | Pilot lab snapshot creates one Success run and one file row per result set; file rows = SP rows = DuckDB COUNT(*). | tests | Integration test | P3-03 | 1 | 19 |  |  |  | Not Started
P6-02 | P6 |  | Live vs snapshot parity test | Snapshot of current week matches live report: totals, first page, sorted page. | tests | Parity test | P5-03 | 1 | 19 |  |  |  | Not Started
P6-03 | P6 |  | Data fidelity tests | Decimals keep precision/scale; dates and NULLs correct. | tests | Tests | P2-11 | 0.5 | 19 |  |  |  | Not Started
P6-04 | P6 |  | Resilience & idempotency tests | Same RunId re-run gives no duplicate rows; blocking storage fails snapshot but not weekly load. | tests | Tests | P3-04, P3-05 | 1 | 19 |  |  |  | Not Started
P6-05 | P6 |  | Retention test | After 7 weekly runs only retained runs and their blobs remain. | tests | Test | P3-06 | 0.5 | 19 |  |  |  | Not Started
P6-06 | P6 |  | Security tests | Other lab's snapshot id -> 404; unknown filter/sort column ignored; values parameterised. | tests | Tests | P4-05, P2-09 | 0.5 | 19 |  |  |  | Not Started
P6-07 | P6 |  | Cache test | Second open of a snapshot is served from cache (no blob download). | tests | Test | P4-03 | 0.25 | 19 |  |  |  | Not Started
P7-01 | P7 |  | Deploy DB + Azure + library to production | Run LRNMaster scripts, provision container/roles/network/lifecycle, deploy worker and web app with snapshots disabled except pilot lab. | Release | Production deployment | P6-01..P6-07 | 1 | 19 |  |  |  | Not Started
P7-02 | P7 |  | Enable writer for pilot lab (2-3 reports) | Turn on for one pilot lab; watch first weekly runs, file sizes, run time. | Release | Pilot running | P7-01 | 0.5 | 19 |  |  |  | Not Started
P7-03 | P7 |  | Client UAT on real past weeks | Users compare snapshots against what they saw; collect defects. | UAT | UAT sign-off | P7-02 | 3 | 19 |  |  |  | Not Started
P7-04 | P7 |  | Fix UAT defects | Resolve issues raised in UAT. | Dev | Fixes | P7-03 | 2 |  |  |  |  | Not Started
P8-01 | P8 |  | Remaining Denial reports | Denial claim report and other denial result sets: mappers, filter parity, selector. | LabMetricsDashboard | Reports migrated | P7-03 | 2 | 19 |  |  |  | Not Started
P8-02 | P8 |  | Claim Line & LIS reports | Mappers, filter parity, selector; check large-grid performance. | LabMetricsDashboard | Reports migrated | P7-03 | 2.5 | 19 |  |  |  | Not Started
P8-03 | P8 |  | Collection, Clinic & Sales Rep summaries | Mappers, filter parity, selector. | LabMetricsDashboard | Reports migrated | P7-03 | 2.5 | 19 |  |  |  | Not Started
P8-04 | P8 |  | Production summaries & Exec summary | Lab / Augustus / NorthWest production summaries, PHI executive summary. | LabMetricsDashboard | Reports migrated | P7-03 | 2.5 | 19 |  |  |  | Not Started
P8-05 | P8 |  | Coding validation & other standard reports | Any remaining reports in the P0 inventory. | LabMetricsDashboard | Reports migrated | P7-03 | 2 | 19 |  |  |  | Not Started
P8-06 | P8 |  | Enable all labs | Turn on snapshots for all labs; monitor file sizes, snapshot run time, cache size. | Release | All labs live | P8-01..P8-05 | 1 | 20 |  |  |  | Not Started
P9-01 | P9 |  | Backfill last weeks (optional) | Reprocess last few week folders into a scratch DB and snapshot from it, if source files still exist, so 5 weeks show on day one. | LRN.MasterFileProcessorWorker | Backfilled snapshots | P8-06 | 2 | 20 |  |  |  | Not Started
P9-02 | P9 |  | Monitoring & alerts | Alert on Failed snapshot runs, missing weekly snapshot, cache size growth. | Ops | Alerts / dashboard | P8-06 | 1 | 20 |  |  |  | Not Started
P9-03 | P9 |  | Developer guide | How to download from Blob (Storage Explorer) and inspect with DuckDB CLI, VS Code viewer, pandas, Power BI; schema-versioning rules. | docs | Dev guide | P8-06 | 0.5 | 17-19 |  |  |  | Not Started
P9-04 | P9 |  | Schema-version process | Document: bump SchemaVersion when columns change, never rewrite old snapshots, version-specific mappers when needed. | docs | Process note | P8-06 | 0.25 | 19 |  |  |  | Not Started

## Test Checklist
# | Test (from design doc p.19) | Covered by Task | Result | Tested By | Date | Notes
1 | Snapshot for a pilot lab creates one Success run and one file row per result set | P6-01 | Not Run
2 | File row count = SP row count = DuckDB COUNT(*) | P6-01 | Not Run
3 | Snapshot of the current week matches the live report (totals, first page, sorted page) | P6-02 | Not Run
4 | Decimals keep precision and scale; dates and NULLs are correct | P6-03 | Not Run
5 | Re-running the same RunId overwrites files with no duplicate index rows | P6-04 | Not Run
6 | Blocking storage access fails the snapshot but not the weekly load | P6-04 | Not Run
7 | After 7 weekly runs only the retained runs and their blobs remain | P6-05 | Not Run
8 | Another lab's snapshot id returns 404 | P6-06 | Not Run
9 | Unknown filter or sort column is ignored; values are parameterised | P6-06 | Not Run
10 | Second open of a snapshot is served from the cache | P6-07 | Not Run

## Assumptions & Questions
# | Type | Item | Answer / Decision
1 | Gap | The doc says LRN.Snapshots is referenced by 'LRN.ReportEngine'; no such project exists in this repo. Plan assumes LRN.MasterFileProcessorWorker (writer) and LabMetricsDashboard (reader).
2 | Gap | The doc's ParquetReportReader supports only equality / IS NULL filters, but it also says live SP filters (date ranges, IN-lists) must be mirrored. Task P2-10 adds those filter types.
3 | Assumption | Pilot = one lab + 2-3 reports (Denial Summary is the doc's example). Pick the pilot lab and the other pilot reports in P0-01.
4 | Assumption | Est. Days are planning estimates for one developer and are not in the doc. Adjust them on 'Task Split'.
5 | Assumption | P8 report groups come from the existing Sql*Repository classes in LabMetricsDashboard/Services; confirm the final list against the P0-01 inventory.
6 | Question | Some SPs may apply user filters inside the SP. Do they need a 'full grain' parameter mode for snapshots? (P0-02)
7 | Question | Is backfill (P9-01) needed? It depends on whether past week source files are still available.
8 | Question | Is a customer-managed key required for compliance (P1-07)?
9 | Out of scope | Changes to the weekly ETL itself, and the raw-table archive (optional, same mechanism), per the doc.